Klimatický rozvrat a média veřejné služby

SGS Project — Task Plan & Phase Overview

Andrea Culková  |  Working document  |  March 2026

# Legend

Each task has a status indicator:

- ✅ DONE — analysis or output already exists, may need review/polish

- 🔄 PARTIAL — work started, code or data exists, needs completion or correction

- ⬜ TODO — not yet started, needs to be built from scratch

- 🆕 NEW — not in original scope, added as a recommended extension

Technology stack: Python (preferred), R (existing code), Flourish / custom Python for visualizations.

All code should be consolidated into a GitHub repository as part of Phase 1.

# Project Overview & Research Questions

The project analyzes transcripts of all Czech Television (ČT) news programs from January 2012 to April 2022 (531,593 documents). The core goal is a corpus-based critical discourse analysis examining how climate change is reported, by whom, and what silences exist.

Three academic articles are the primary deliverables:

- Article 1 — Triple Silences: Social issues, geographical oversight, and climate change

- Article 2 — Who is and isn't heard: Visibility and marginalization of actors in climate coverage

- Article 3 — Does a decade of ČT news fulfill Transformative Journalism values?

Core datasets available:

- Whole corpus: 531,593 news documents (2012–2022)

- Climate subcorpus v4: 2,914 documents (bi/trigram filtered)

- Social/poverty subcorpus: 4,853 documents

- Motorist subcorpus: 63,496 documents

- SIC subcorpus: large CSV (551 MB) — terrorism/security topic

- COVID subcorpus: exists locally

# PHASE 0 — Infrastructure & Audit (Do This First)

Purpose: Before any new analysis, get everything organized. Without this, work is fragmented, unreproducible, and hard to hand off. This phase has no research output on its own but makes everything else possible.

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| P0.1 | Set up GitHub repository — create repo, organize folders by subcorpus and analysis type, commit all existing local code (R and Python) | ⬜ TODO | Folder structure: /data, /corpora, /analysis/article1, /analysis/article2, /analysis/article3, /visualizations, /utils |
| P0.2 | Document all existing corpus files — record exact filenames, sizes, versions, creation dates, and what cleaning steps were applied to each | ⬜ TODO | Produces: CORPORA_INVENTORY.md — a single source of truth for all data files |
| P0.3 | Audit existing code — collect all R and Python scripts, annotate what each does, flag which are broken or outdated | ⬜ TODO | Convert existing R scripts to Python where feasible; keep R for anything that's working and complex to rewrite |
| P0.4 | Confirm all subcorpora are accessible and loadable in Python — test reading climate_corpus_v4.csv, sic_articles_truncated.csv, and all other files | ⬜ TODO | Produces: simple data_check.py script that verifies all files load correctly with row counts |
| P0.5 | Identify what the SIC subcorpus actually contains — check if it's terrorism/security or social issues corpus; it may be the missing social subcorpus | ⬜ TODO | SIC = 551MB which is large for a subcorpus; clarify what keywords were used to build it |

# PHASE 1 — Data Foundations (Corpora & Geography)

Purpose: Ensure all subcorpora are clean, correctly built, and the geographic/country analysis is error-free. This feeds Articles 1 and 3, and the FAMU public page. All of Article 1 (Triple Silences) can be completed in this phase.

## 1A — Subcorpora Audit & Completion

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| P1.1 | Review climate subcorpus v4 — verify the current state matches the bi/trigram keyword list shown in the Poznan presentation; document any gaps | 🔄 PARTIAL | v4 with 2,914 docs exists; check that the 'klimatický podmínky' exclusion (X-coded documents) was properly applied |
| P1.2 | Confirm social/poverty subcorpus (4,853 docs) — verify it is correctly built with all the keywords (chudoba*, bezdomovectví, sociální vyloučení, etc.) and loaded in Python | 🔄 PARTIAL | Exists per Poznan presentation; check if Irene Elmerot's results are accessible and consistent with current files |
| P1.3 | Confirm motorist subcorpus (63,496 docs) — verify keywords include Spalovac* Motor*, Elektrick* Motor*, and all transport/road terms | ✅ DONE | Shown in Poznan presentation with correct keyword list |
| P1.4 | Confirm COVID subcorpus — load from local drive, document keyword list and size | ⬜ TODO | COVID corpus visible in NMF 20 results as Topic 5; build from full corpus if not already extracted as separate file |
| P1.5 | Confirm terrorism/SIC subcorpus — load sic_articles_truncated.csv, document keyword list and verify it matches terrorism/security topic (NMF Topic 16) | ⬜ TODO | sic_articles_truncated.csv is 551MB; could be the terror corpus or the social corpus — must verify |
| P1.6 | Build subcorpus size comparison table — document counts and % of total corpus for all 5 subcorpora | 🔄 PARTIAL | Bar chart exists in Poznan presentation for climate/motor/social; needs to be a reproducible Python script outputting a clean table |

## 1B — Geographic / Country Analysis (fix errors)

This analysis was done but Andrea flagged errors due to variant country name forms (e.g., 'Německo' vs 'německý', 'USA' vs 'Spojené státy' vs 'americký'). The task is to rebuild it properly with AI-assisted entity normalization.

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| P1.7 | Build comprehensive country name lookup table — collect all variant forms for each country in Czech (official name, adjective, demonym, abbreviations, historical names) | ⬜ TODO | Use LLM API to generate variant forms per country; cross-check against the existing named entity lists from the project; output: country_variants.csv |
| P1.8 | Re-run country mention detection on whole corpus using the corrected lookup table — map all variants to canonical country names, assign World Bank GNI category | 🔄 PARTIAL | Previous analysis exists but has errors; rerun with country_variants.csv; use the World Bank GNI 2022 list for categories |
| P1.9 | Re-run country mention detection on climate subcorpus v4 — same process as P1.8 but restricted to climate documents | 🔄 PARTIAL | Previous charts shown in Poznan (yearly GNI counts for whole corpus and climate subcorpus); needs correction and reproducible code |
| P1.10 | Special check: Palestine vs Israel disproportion — the doc notes this is visible; verify the counts and flag it explicitly in the output data | ⬜ TODO | Noted by Andrea as particularly striking; confirm numbers, document in output table |
| P1.11 | Produce geographic 'blind spots' map — global map showing countries with <100 mentions over 10 years vs high salience countries; separate maps for whole corpus and climate subcorpus | 🔄 PARTIAL | Concept shown in project doc; existing GNI bar charts done; world map visualization still needed |
| P1.12 | Produce yearly GNI category trend charts — line charts showing yearly mention counts by income category (whole corpus + climate subcorpus) | ✅ DONE | Both charts shown in Poznan presentation; need to reproduce in Python with corrected data |

## 1C — Subcorpus Frequency & Time Trend Visualizations

These are the core 'Triple Silences' visualizations for Article 1. Most exist but need to be reproduced in Python from corrected data, styled consistently, and exported for Flourish or publication.

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| P1.13 | Reproduce subcorpus size bar chart (absolute counts) — Python/matplotlib or Flourish; all 5 subcorpora vs total corpus | 🔄 PARTIAL | R chart exists in Poznan; reproduce in Python with corrected data including COVID and terror |
| P1.14 | Reproduce time-series chart — % of documents per month containing climate/social/motor/terror/COVID terms, 2012–2022 | ✅ DONE | Chart shown in Poznan; reproduce in Python; verify data is from corrected subcorpora |
| P1.15 | Create per-article (doc-level) frequency tables for each subcorpus — output CSV with doc-id, date, show name, term count | ⬜ TODO | Needed as input for actor analysis in Phase 2 — identifies which docs in climate subcorpus have speakers |

# PHASE 2 — Actor Detection & Classification (Article 2)

Purpose: Identify and classify all speakers in the climate subcorpus. This is the core of Article 2. Speaker detection (named entity recognition) was done on the whole corpus, but the classification into M1–M6 categories has not been done. This phase requires LLM API calls.

## 2A — Speaker Detection

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| P2.1 | Review existing named entity recognition results — load the entity lists and proper noun lists from local drive; document their format, coverage, and quality | 🔄 PARTIAL | Named entity detection was done on the whole corpus; needs to be assessed for the climate subcorpus specifically |
| P2.2 | Re-run or validate speaker detection on climate subcorpus v4 — extract all instances of 'Jméno PŘÍJMENÍ' patterns (person names in ALL CAPS surname format as used in transcripts) | 🔄 PARTIAL | Methodology: regex + NER; transcripts use a specific format where speaker names appear with their title/organization in a characteristic pattern |
| P2.3 | For each detected speaker, extract the 5 required fields: doc-id, full name, profession/organization description (from transcript), speaker type M1–M6, gender | ⬜ TODO | Fields defined in project spec; profession/org description is available in transcript immediately after the name |
| P2.4 | Classify all speakers into M1–M6 categories using LLM API — send name + profession/org description to API; prompt must include category definitions from project documentation | ⬜ TODO | Categories: M1=Moderátor, M2=Občan, M3=Vědec, M4=Popularizátor/Pseudovědec, M5=Stakeholder, M6=Politik; use batch API calls to minimize cost; estimate ~2,914 docs |
| P2.5 | Classify gender for each speaker — use LLM API with Czech name + context; flag ambiguous cases for manual review | ⬜ TODO | Output: gender column (M/F/unknown); Czech names are usually gender-obvious but foreign names may need context |
| P2.6 | Validate a random sample of ~100 speaker classifications manually — calculate inter-annotator reliability proxy; adjust prompt if needed | ⬜ TODO | Quality gate: if >85% agreement with manual annotation, classifications are acceptable |
| P2.7 | Produce master speaker table — CSV with all speakers, all 5 fields, deduplicated by person name where same person appears in multiple docs | ⬜ TODO | Output: speakers_climate.csv — this is the key input for all Article 2 visualizations |

## 2B — Actor Salience & Marginalization Analysis

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| P2.8 | Calculate speaker salience scores — count total mentions per speaker, per speaker type (M1–M6), and per year; rank by frequency | ⬜ TODO | Output: salience_by_speaker.csv, salience_by_type_year.csv |
| P2.9 | Identify marginalized actors — speakers/types that appear very rarely; identify under-represented categories (e.g., are citizens M2 and scientists M3 rare vs politicians M6?) | ⬜ TODO | Key finding for Article 2: is ČT elitist — dominated by political elites? |
| P2.10 | Visualize speaker type distribution — stacked bar or pie chart of M1–M6 share of total speaker appearances; time trend version (by year) | ⬜ TODO | Flourish or Python; 2 charts: overall distribution + yearly evolution |
| P2.11 | Visualize gender breakdown by speaker type — show M/F ratio within each M1–M6 category | ⬜ TODO | 1 chart; highlight any strong gender imbalances |
| P2.12 | Visualize top 20 most mentioned speakers overall — horizontal bar chart | ⬜ TODO | 1 chart; label with name + type + short org description |

# PHASE 3 — Stance, Topic Modeling & Transformative Journalism Analysis (Article 3)

Purpose: This is the most complex phase, building on Phase 2. It adds stance coding (S1–S6) to speakers, runs topic modeling on the climate subcorpus, analyzes polarization, and evaluates the corpus against Transformative Journalism criteria. This is the core of Article 3.

## 3A — Stance Coding (S1–S6)

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| P3.1 | Define stance classification prompt — write a detailed LLM prompt for S1–S6 classification using the full category definitions from project documentation; test on 20 manually coded examples | ⬜ TODO | S1=Denier, S2=Manipulator, S3=Delayer, S4=Techno-optimist, S5=Market fundamentalist, S6=Informer; prompt must include key indicators and Czech-language examples |
| P3.2 | Run stance classification on all speakers in climate subcorpus — for each speaker occurrence, send: doc-id + speaker name + profession + surrounding text context (±200 words) to LLM API | ⬜ TODO | Output adds 6th column to master speaker table; each speaker occurrence gets a stance code; same person may have different stances in different docs |
| P3.3 | Validate stance classifications — manually review 150 cases (25 per category); adjust prompt if precision <80% | ⬜ TODO | Quality gate before using results for publication |
| P3.4 | Analyze stance distribution — frequency table of S1–S6 across all speaker occurrences; breakdown by speaker type M1–M6 | ⬜ TODO | Key finding: what proportion of climate speakers are deniers, delayers, vs informers? |
| P3.5 | Polarization analysis — for each document (doc-id), check if speakers with contradictory stances appear together (e.g., S1 Denier + S6 Informer in same story); flag as 'false balance' | ⬜ TODO | Key finding for Article 3: is ČT creating false equivalence between climate science and denial? |
| P3.6 | Visualize stance distribution — stacked bar chart; heatmap of M-type × S-type co-occurrence | ⬜ TODO | 2 charts |

## 3B — Topic Modeling on Climate Subcorpus

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| P3.7 | Prepare climate subcorpus for topic modeling — lemmatize using Czech lemmatizer (MorfFlex or equivalent), build document-term matrix, filter stopwords and low-frequency terms | 🔄 PARTIAL | Library of 2,910 words already exists from whole-corpus analysis; reuse and adapt for climate subcorpus; with only 2,914 docs, modeling will be faster |
| P3.8 | Run NMF models (20, 25, 30, 35, 40, 50 topics) on climate subcorpus — compute coherence scores | ⬜ TODO | Note: whole-corpus NMF 20 showed NO climate topic — that was the key finding. Climate subcorpus topic modeling will show what climate coverage is actually about. |
| P3.9 | Run LDA models (same range) on climate subcorpus — compute coherence at λ=0.6 | ⬜ TODO | Compare with NMF; use the existing climate-topics.netlify.app approach as reference |
| P3.10 | Select best model — manually validate top models; select most coherent and interpretable; label each topic | ⬜ TODO | Likely output: NMF 20–30 topics; priority labels: nuclear energy, renewables, drought/floods, health impacts, EU Green Deal |
| P3.11 | Identify mitigation vs adaptation topics — for each topic, classify whether it is primarily about mitigation (reducing emissions) or adaptation (coping with effects) | ⬜ TODO | Key finding for Article 3: is ČT more focused on adaptation (floods, drought) than mitigation (decarbonization)? |
| P3.12 | Link topics to speakers — join topic model output (doc-id → topic) with speaker table (doc-id → speaker, type, stance); enable analysis of who speaks about which topics | ⬜ TODO | This is the crucial analytical linkage between Phases 2 and 3 |
| P3.13 | Visualize topic model — interactive pyLDAvis or Flourish; topic × speaker-type heatmap; topic × stance heatmap | ⬜ TODO | 3 visualizations; can reuse/adapt the existing climate-topics.netlify.app |

## 3C — Urgency, Mitigation vs Adaptation, Planetary Limits (Frequency Analysis)

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| P3.14 | Extend existing frequency analysis code — add new keyword groups: urgency terms (naléhavost, krize, hrozba, okamžitě, kolaps), planetary limits terms (planetární limity), fossil fuel terms (fosilní paliva, uhlí), net-zero/carbon neutral terms | 🔄 PARTIAL | Code for frequency analysis exists; needs extension with new term lists from project spec |
| P3.15 | Run extended frequency analysis on climate subcorpus — output: yearly frequency of each keyword group, concordance samples | ⬜ TODO | Output: frequency_urgency.csv, frequency_mitigation.csv; both absolute counts and per-document normalized |
| P3.16 | Collocate analysis — what words co-occur with 'klimatická změna', 'globální oteplování', 'riziko', 'krize' in the climate subcorpus? | ⬜ TODO | Use Python (NLTK or spaCy) or Sketch Engine if available; produces collocate tables |
| P3.17 | Visualize urgency/mitigation trends — line chart showing urgency term frequency per year in climate subcorpus | ⬜ TODO | 1 chart |

## 3D — Transformative Journalism Assessment

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| P3.18 | Operationalize TJ criteria as measurable indicators — map the 3 TJ principles (De-polarization, Urgency Building, Just Transformation) to specific measurable outputs from Phases 2 and 3 | ⬜ TODO | e.g., De-polarization = % of docs with false balance (P3.5); Urgency Building = frequency of urgency terms (P3.14); Just Transformation = proportion of M2 citizens and social justice framing |
| P3.19 | Produce TJ assessment summary table — for each criterion, state the finding, the evidence, and whether ČT meets, partially meets, or does not meet the criterion | ⬜ TODO | This is the synthesis that drives Article 3 conclusions |

# PHASE 4 — Case Studies (Article 3, Section D)

Purpose: Three in-depth discourse analyses of specific topics within the climate subcorpus. These are qualitative deep dives that complement the quantitative findings. They require identifying relevant documents using doc-id linkage from Phase 3.

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| P4.1 | Case Study 1: Nuclear energy & renewables (OZE) — identify all climate subcorpus documents containing these topics (via topic model from P3.10 or keyword search); analyze framing, speaker types, and stances | ⬜ TODO | Expected to be one of the highest-frequency topics in the climate subcorpus; analysis: is nuclear presented as climate solution? Are renewables framed negatively? |
| P4.2 | Case Study 2: Drought and floods — same process; analyze how extreme weather events are covered and whether they are connected to climate change or treated as isolated events | ⬜ TODO | Key TJ criterion: 'restorative narrative' — are adaptation and mitigation mentioned together? |
| P4.3 | Case Study 3: Health impacts of climate change — identify documents using keyword 'zdraví' + climate context; this is expected to be the marginalized topic (almost absent) | ⬜ TODO | Expected to be nearly invisible — the absence itself is the finding; document how few articles exist and what little coverage says |
| P4.4 | For each case study: produce a discourse analysis narrative with 3–5 illustrative excerpts; apply TJ framework as analytical lens | ⬜ TODO | Output: qualitative text sections for Article 3; 3–6 pages each |

# PHASE 5 — Visual Unification & FAMU Public Page

Purpose: All analytical outputs from Phases 1–4 need to be visually unified and presented on a publicly accessible FAMU subpage. This phase ensures the research is communicated effectively as a coherent whole.

## 5A — Visual Style Guide

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| P5.1 | Define unified visual style — color palette, typography, chart template for all visualizations (consistent with Poznan presentation aesthetic: dark red #8B1A1A, cream background, bold sans-serif) | ⬜ TODO | Output: style_guide.md + Python matplotlib/seaborn template file; Flourish theme settings |
| P5.2 | Reproduce all existing charts in the new unified style — recreate all Poznan presentation charts in Python using the new template | 🔄 PARTIAL | Charts exist as images; need reproducible Python code versions |

## 5B — Visualization Inventory (complete list)

All visualizations needed across the three articles:

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| V1 | Subcorpus size comparison bar chart (whole corpus context) | 🔄 PARTIAL | Article 1 / FAMU page |
| V2 | Time series: % of docs per month by subcorpus topic (climate/social/motor/terror/covid) | ✅ DONE | Article 1 / FAMU page |
| V3 | World map: country mention blind spots (whole corpus) | ⬜ TODO | Article 1 / FAMU page |
| V4 | World map: country mention blind spots (climate subcorpus) | ⬜ TODO | Article 1 / FAMU page |
| V5 | GNI category yearly trend — whole corpus | ✅ DONE | Article 1 / FAMU page |
| V6 | GNI category yearly trend — climate subcorpus | ✅ DONE | Article 1 / FAMU page |
| V7 | GNI total mentions bar chart — whole corpus | ✅ DONE | Article 1 / FAMU page |
| V8 | GNI total mentions bar chart — climate subcorpus (normalized) | ✅ DONE | Article 1 / FAMU page |
| V9 | Speaker type (M1–M6) overall distribution | ⬜ TODO | Article 2 / FAMU page |
| V10 | Speaker type yearly evolution (stacked area) | ⬜ TODO | Article 2 / FAMU page |
| V11 | Gender breakdown by speaker type | ⬜ TODO | Article 2 / FAMU page |
| V12 | Top 20 most mentioned climate speakers (horizontal bar) | ⬜ TODO | Article 2 / FAMU page |
| V13 | Stance distribution (S1–S6) overall | ⬜ TODO | Article 3 / FAMU page |
| V14 | Speaker type × stance heatmap | ⬜ TODO | Article 3 / FAMU page |
| V15 | Topic model visualization (climate subcorpus) | ⬜ TODO | Article 3 / FAMU page |
| V16 | Topic × speaker type heatmap | ⬜ TODO | Article 3 / FAMU page |
| V17 | Urgency/mitigation keyword frequency over time | ⬜ TODO | Article 3 / FAMU page |
| V18 | Mitigation vs adaptation topic proportions | ⬜ TODO | Article 3 / FAMU page |

## 5C — FAMU Public Page

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| P5.3 | Design page structure — define sections, which visualizations appear, in what order, with what explanatory text (in Czech) | ⬜ TODO | Page should tell the story: how much does ČT cover climate? Who speaks? What stances? What silences? |
| P5.4 | Build or configure the FAMU subpage — embed Flourish visualizations, add narrative text, ensure mobile-friendly layout | ⬜ TODO | Coordinate with FAMU web team; Flourish embeds work in most CMS systems |
| P5.5 | Write Czech explanatory texts for each visualization — accessible to general public, not academic | ⬜ TODO | Each chart needs a 2–3 sentence caption explaining what it shows and why it matters |

# PHASE 6 — Optional: Brussels / European Green Policy Analysis

This is an additional subproject suggested by Andrea. It is not part of the three core articles but could be a fourth article or supplementary analysis.

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| P6.1 | Build 'Brussels/EU Green Policy' subcorpus — extract documents from the full corpus containing EU climate policy terms: Green Deal, Fit for 55, ETS, EU taxonomy, combustion engine ban, Brusel, Zelená dohoda, etc. | 🆕 NEW | Expected to be a small but important subcorpus; will likely reveal how EU climate policy is framed — as threat or opportunity |
| P6.2 | Sentiment analysis on EU climate policy subcorpus — classify each document as positive/neutral/negative toward EU climate policy; use LLM API | 🆕 NEW | Key question: is Brussels/Green Deal presented as friend or enemy in ČT coverage? |
| P6.3 | Temporal analysis — how does sentiment toward EU climate policy change over time? Does it shift with political cycles (e.g., after ODS/SPOLU election victory)? | 🆕 NEW | Would connect climate media coverage to Czech political context |
| P6.4 | Actor analysis — who are the speakers in EU climate policy stories? Are they the same political elite as in general climate coverage? | 🆕 NEW | Cross-reference with master speaker table from Phase 2 |

# Dependency Map — What Must Be Done Before What

Read this before starting work to understand the critical path:

P0 (Infrastructure) → everything else. Nothing should be started until P0 is done.

- P0 → P1A (subcorpora confirmed) → P1B (geography fixed) → P1C (Article 1 visualizations)

- P0 → P1A → P2A (speaker detection) → P2B (salience analysis) → Article 2

- P2A → P3A (stance coding needs speakers) → P3B (topic model) → P3C → P3D → Article 3

- P3B (topic model with doc-ids) → P4 (case studies need topic-tagged docs)

- P1–P4 → P5 (all analysis must be done before unification and FAMU page)

- P2A (master speaker table) → P6 (optional Brussels analysis uses same speakers)

Critical path for Article 1: P0 → P1A → P1B → P1C → write Article 1

Critical path for Article 2: P0 → P1A → P2A → P2B → write Article 2

Critical path for Article 3: P0 → P1A → P2A → P3A → P3B → P3C → P3D → P4 → write Article 3

# Open Questions — Clarification Needed

| ID | Task | Status | Notes / Output |
| --- | --- | --- | --- |
| Q1 | What exactly is in the SIC subcorpus? Is it terrorism/security, or is it the social issues corpus, or something else? | ⬜ TODO | Need to open sic_articles_truncated.csv and check the content to confirm |
| Q2 | Is the COVID subcorpus a separate file, or does it need to be extracted from the full corpus using keyword matching? | ⬜ TODO | If it's only available via the full corpus, need access to the full 531,593-document dataset |
| Q3 | What is the current format of the named entity / proper noun lists from the entity recognition work? (CSV, JSON, plain text?) Are they organized by subcorpus or by the whole corpus? | ⬜ TODO | Determines how much preprocessing is needed before P2.1 |
| Q4 | Does Andrea have access to the Sketch Engine instance where the corpus was loaded, or is all work now done locally from CSV files? | ⬜ TODO | If Sketch Engine is available, some concordance/collocation tasks are much easier |
| Q5 | For the FAMU public page — is there an existing web infrastructure, or does it need to be built from scratch? Who is the technical contact at FAMU? | ⬜ TODO | Affects scope of Phase 5 |

Document prepared March 2026. This is a living working document — update task statuses as work progresses.